## Tabelle1
Date | time axis 2012-04-23 to 2012-08-05
Calendar week | 2012-04-23: cw17; 2012-04-30: cw18; 2012-05-07: cw19; 2012-05-14: cw20; 2012-05-21: cw21; 2012-05-28: cw22; 2012-06-04: cw23; 2012-07-05: cw27; 2012-07-09: cw28; 2012-07-16: cw29; 2012-07-23: cw30; 2012-07-30: cw31
Energizing of 110/31.5kV Mihai Viteazu Substation | bar: 2012-07-05 to 2012-07-07
Energizing the 31.5kV cable grid through turbines | bar: 2012-07-06 to 2012-07-08
Commissioning of wind turbines: | bar: 2012-07-09 to 2012-07-21
Commissioning turbine 033 | bar: 2012-07-09 to 2012-07-13
Commissioning turbine 032 | bar: 2012-07-12 to 2012-07-14; 2012-07-16
Commissioning turbine 031 | bar: 2012-07-13 to 2012-07-14; 2012-07-16 to 2012-07-17
Commissioning turbine 030 | bar: 2012-07-14; 2012-07-16 to 2012-07-18
Commissioning turbine 041 | bar: 2012-07-16 to 2012-07-19
Commissioning turbine 040 | bar: 2012-07-18 to 2012-07-21
Start in-house tests (with ICEMENERG) | bar: 2012-07-23
Record of wind farm behaviour (with ICEMENERG) | bar: 2012-07-23 to 2012-07-28; 2012-07-30 to 2012-08-03
* Depending on wind behaviour & each turbine technical characteristics
** Start and duration depending on wind behaviour and availability of Icemenerg and Enercon